## Sheet1
Task | Notes
Pre Reorg Implementaion tasks
Review/Adjust database conect strings to include xhepydbm1p
create golden gate file systems on xheplydbm21p
Install Golden Gate Software on xhepydbm21p
Configure GG and HEPYPRD DB on xhepydbm21p
drop disk groups on xhepydbm1p
resize asm disks on xhepydbm1p
recreate disk groups on xhepydbm1p
Build HEPYPRD database on xhepydbm1p - execute clone_sbdb script - patch database to 19.12.1 (execute datapatch) - create pfile from spfile on source, copy and modify to target - create tablespaces - resize redo logs - resize temp tablespace - resize undo tablespace - disable checksums - disable stats jobs - disable force logging - disable pga limit - create datapump directory - disable archivelog mode - create ggadmin user - enable gg database replication - add sequence support - alter awr snaphots - alter maintenance windows on xhepydbm1p - alter autostat preferances on xhepydbm1p
configure GG mgr parameters for on xhempydbm1p to commuicate with xhepydbm21p
create import par file with excluded indexes
create export par file
pack sqlprofiles and baselines on xhepydbm21p
Reorg Implementation Tasks
enable supplmental logging on xhepydbm21p | ALTER DATABASE ADD SUPPLEMENTAL LOG DATA;
add schema tran data for PROD on xhepydbm21p | add schematrandata prod
add schema tran data for HE_CUSTOM on xhepydbm21p | add schematrandata he_custom
add supplemental log data for sequence support on xhepydbm21p | ALTER TABLE sys.seq$ ADD SUPPLEMENTAL LOG DATA (PRIMARY KEY) COLUMNS;
add sequence support on xhepydbm21p | @sequence.sql
register extract on xhepydbm21p | register extract ehrp, database
add extract on xhepydbm21p | add extract ehrp, integrated tranlog, begin now
add extract trail on xhepydbm21p | add exttrail /oraggdata/dirdat/et, extract ehrp, megabytes 2000
add pump on xhepydbm21p | add extract phrp, exttrailsource /oraggdata/dirdat/et
add remote trail on xhepydbm21p | add rmttrail /oraggdata/dirdat/rt, extract phrp, megabytes 2000
add checkpoint table on xhepydbm1p | add checkpointtable ggadmin.chktbl
add rhrp replicat on xhepydbm21p | add replicat RHRP PARALLEL exttrail /oraggdata/dirdat/rt checkpointtable ggadmin.chktbl
add rhec replicat on xhepydbm21p | add replicat RHEC PARALLEL exttrail /oraggdata/dirdat/rt checkpointtable ggadmin.chktbl
add rflc replicat on xhepydbm21p | add replicat RHEC PARALLEL exttrail /oraggdata/dirdat/rt checkpointtable ggadmin.chktbl
start extract on xhepydbm21p | start extract ehrp
start pump on xhepydbm21p | start extract phrp
check for long running transactions on xhepydbm21p | select sid, serial#, start_time from v$session sess, v$transaction ts where ts.ADDR=
wait for any long running transactions to complete
get current scn | select current_scn from v$database;
alter export parm file with flashback scn from previous step | /tmpshrs/hrpreorgTEMP/HEPYPRD/export_hepyprd.par
alter undo retention to 28800 on xhepydbm21p
start export on xhepydbm21p | expdp <user id> parfile=export_hepyprd.par
start import on xhepydbm1p | impdp <user id> parfile=import_hepyprd.par
alter undo retention to 6400 on xhepydbm21p
execute grants on hepydbm1p | grant_dbms_lock.sql, grant_oltp_role.sql
correct nologging on indexes
recompile invalid objects on xhepydbm1p | ?/rdbms/admin/utlrp
enable checksums on xhepydbm1p | $ORACLE_BASE/admin/enable_checksums.sql
start rhrp replicat with after csn from step 22 on xoracldm1p | start replicat rhrp aftercsn <scn from step 25>
start rhec replicat with after csn from step 22 on xoracldm1p | start replicat rhec aftercsn <scn from step 25>
start rflc replicat with after csn from step 22 on xoracldm1p | start replicat rflc aftercsn <scn from step 25>
execute rman to check for block corruption | check_logical_curruption.sh
enable autostats | enable_stats_jobs.sql
Wait for replicats to sync
Pre Switch Over Tasks
unpack profiles and baselines on xhepydbm1p | unpack_profile_baseslines.sql
build excluded online indexes on xhepydbm1p | build_indexes.sh > build_indexes.out
execute autostats on xhepydbm1p
stop rhrp replicat on xhepydbm1p | stop rhrp
stop rhec replicat on xhepydbm1p | stop rhec
stop rflc replicat on xhepydbm1p | stop rflc
build excluded offline indexes on xhepydbm1p | build_offline_indexes.sh
enable archivelog mode on xhepydbm1p
enable pga limit | enable_pga_limit.sql
enable force logging on xhepydbm1p | enable_force_logging.sql
enable supplmental logging on xhepydbm1p | enable_supplemental_logging.sql
add supplemental log data for sequence support on xhepydbm1p | ALTER TABLE sys.seq$ ADD SUPPLEMENTAL LOG DATA (PRIMARY KEY) COLUMNS;
start rhrp replicat on xhepydbm1p | start rhrp
start rhec replicat on xhepydbm1p | start rhec
start rflc replicat on xhepydbm1p | start rflc
schedule backups for xhepydbm1p in OEM
deploy oem montoring template from xhepydbm21p to xhepydbm1p
add schema tran data for PROD on xhepydbm1p | add schematrandata prod
add schema tran data for HE_CUSTOM on xhepydbm1p | add schematrandata he_custom
add supplemental log data for sequence support on xhepydbm1p | ALTER TABLE sys.seq$ ADD SUPPLEMENTAL LOG DATA (PRIMARY KEY) COLUMNS;
Switch Over Tasks
Shutdown application
allow replicats to sync
stop replicat rhrp on xhepydbm1p | stop rhrp
stop replicat rhec on xhepydbm1p | stop rhec
stop replicat rflc on xhepydbm1p | stop rflc
register extract on xhepdbm1p | register extract ehrp, database
add extract on xhepydbm1p | add extract ehrp, integrated tranlog, begin now
add extract trail on xhepydbm1p | add exttrail /oraggdata/dirdat/et, extract ehrp, megabytes 2000
add pump on xhepdydbm1p | add extract phrp, exttrailsource /oraggdata/dirdat/et
add remote trail on xhepdydbm1p | add rmttrail /oraggdata/dirdat/rt, extract phrp, megabytes 2000
grant dba to ggadmin on xhepydbm21p
add checkpoint table for replicats on xhepydbm21p | add checkpointtable ggadmin.chktbl
add replicat rhrp on xhepydbm21p | add replicat RHRP PARALLEL exttrail /oraggdata/dirdat/rt checkpointtable ggadmin.chktbl
add replicat rhec on xhepydbm21p | add replicat RHEC PARALLEL exttrail /oraggdata/dirdat/rt checkpointtable ggadmin.chktbl
add replicat rflc on xhepydbm21p | add replicat RFLC PARALLEL exttrail /oraggdata/dirdat/rt checkpointtable ggadmin.chktbl
export sequences from xhepydbm21p
drop seqences on xhepydbm1p
import sequencces on xhepydbm1p
start extract on xhepydbm1p | start ehrp
start pump on xhepydbm1p | start phrp
start rhrp replicat on xhepydbm21p | start rhrp
start rhec replicat on xhepydbm21p | start rhec
start rflc replicat on xhep | start rflc
switch hepyprd listener port to 1574 on xhepydbm1p
stop hepyprd_app service on xhepydbm21p and disable startup trigger
startup application
Post Switch Over Tasks
stop extract on xhepydbm1p | stop ehrp
stop pump on xhepydbm1p | stop phrp
delete extract on xhepydbm1p | delete extract ehrp
delete pump on xhepydbm1p | delete extract phrp
unregister extract on xhepydbm1p | unregister extract ehrp database
stop replicat rhrp on xhepydbm21p | stop rhrp
stop replicat rhec on xhepydbm21p | stop rhec
stop replicat rflc on xhepydbm21p | stop rflc
delete replicat rhrp on xhepydbm21p | delete replicat rhrp
delete replicat rhec on xhepydbm21p | delete replicat rhec
delete replicat rflc on xhepydbm21p | delete replicat rflc
stop mgr on xhepydbm1p | stop mgr
stop mgr on xhepydbm21p | stop mgr
disable gg replication | alter system set ENABLE_GOLDENGATE_REPLICATION=FALSE
disable supplemental logging on xhepydbm1p
ALTER DATABASE DROP SUPPLEMENTAL LOG DATA (PRIMARY KEY) COLUMNS;
ALTER DATABASE DROP SUPPLEMENTAL LOG DATA (UNIQUE) COLUMNS;
ALTER DATABASE DROP SUPPLEMENTAL LOG DATA;
drop user ggadmin on xhepydbm1p
drop directory datapump_reorg on xhepydbm1p
drop stanby database on xhepydbw21p
re-create disk groups on xhepydbw21p
create standby database on xhepydbw21p
de-install GG software on xhepydbm1p
remove /oragg and /oraggdata file systems
remove /tmpshrs/hrpreorgTEMP file share
Backout Tasks
shutdown application
ensure databases are in sync (zero lag)
stop extract on xhepydbm1p
stop pump on xhepydbm1p
stop replicat rhrp on xhepydbm21p
stop replicat rhec on xhepydbm21p
stop replicat rflc on xhepdybm21p
enable service and trigger on xhepydbm21p
disable service and trigger on xhepydbm1p
start application
delete extract on xhepydbm1p
delete pump on xhepdydbm1p
unregister extract on xhepydbm1p