## WKAB DBAR TEST Plan
WKAB DBAR Exercise - Test Plan Timeline
Task Number | Task Description | Resource | Est. Duration | Est. Start Time | Est. Completion | Actual Start Time | Actual Completion Time | Actual Duration
Date / Time of DBAR Test: | 2013-07-11
Application Name: | WKAB
Domain: | Informatics, Medical Mgmt. and Corporate
TABoR APP ID | 2135
REMEDY CHANGE Ticket : | CRQ35676
DBAR Conference Line: | 1(203) 607-0564 PC 342-1269
Database Name/Instance: | Aetnaprod & Spnode45 / WKABPROD DB and DPPRD01 DB
Size of Database:
Platform: | AIX, ORACLE
Production DB Server Name(s): | Aetnaprod & Spnode45
DBAR DB Server Name(s):
1 | DRPS Administration TASKS | Resource | Est. Duration | Est. Start Time | Est. Completion | Actual Start Time | Actual Completion Time | Actual Duration
2 | Conduct intial meeting with stakeholders | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
3 | Establish the DBAR team | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
4 | Determine a meeting schedule | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
5 | Create an REMEDY Change # | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
6 | Request a schema of the application (if applicable) | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
7 | Create a scope and objectives document | DBAR Team | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
8 | Review scope and objectives document and obtain official sign-off from team | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
9 | Discuss documentation needed with Internal Audit | DBAR Team | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
10 | Document & Review Test Timeline (Test plan) with Team | DBAR Team | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
11 | Document & Review Business Checkout plan with application/business checkout team | DBAR Team | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
12 | Create a contact list to include the DBAR team and their Aetna ID's | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
13 | Obtain conference line for day of test | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
14 | Ensure DBAR Plan is available | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
15 | Distribute all test related documentation to Team | DRPS | 5 | 2013-07-01 08:00 | 2013-07-01 13:00 | 2013-07-01 08:00 | 2013-07-01 13:00 | 5
16 | PRE-TEST TASKS | Resource | Est. Duration | Est. Start Time | Est. Completion | Actual Start Time | Actual Completion Time | Actual Duration
17 | Acquire WCC Test servers for Aetnaprod & Spnode45 | AIX Eng | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
18 | Aquire WCC Web Server | Web Eng | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
19 | Build (PROD) specifications | AIX Eng | 2 | 2013-07-01 08:00 | 2013-07-01 10:00 | 2013-07-01 08:00 | 2013-07-01 10:00 | 2
20 | Tasks associated with Midrange storage | MID STORMAN | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
21 | Verify WKABPROD DB configuration to build | DBA | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
22 | Verify DPPRD01 DB configuration to build | DBA | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
23 | Obtain and validate from DBA area all WKAB user login accounts for WKAB's DBAR environment. | DBA | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
24 | Build AIX LPAR in remote location | Server Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
25 | Clone the production server to the DBAR Server | Server Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
26 | Configure the security access from the authorized DBAR server names above | Server Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
27 | Contact the SSS storage engineer for hand off of DBAR server for storage configuration | Server Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
28 | Verify Switch Zoning, modify if necessary | Storage Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
29 | Build the DASD Connections to the test server | Storage Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
30 | Import the LUN's onto the server | Storage Engineer | 0 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 2013-07-01 08:00 | 0
31 | Verify that the PVID numbers of the LUN's match production | Storage Engineer | 0.5 | 2013-07-01 08:00 | 2013-07-01 08:30 | 2013-07-01 08:00 | 2013-07-01 08:30 | 0.5
32 | Create test scripts to execute on DBAR server | DBA | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
33 | Execute test scripts on production to verify output on the DBAR server | DBA | 1 | 2013-07-01 08:00 | 2013-07-01 09:00 | 2013-07-01 08:00 | 2013-07-01 09:00 | 1
34 | DBAR EXERCISE EXECUTION | Resource | Est. Duration | Est. Start Time | Est. Completion | Actual Start Time | Actual Completion Time | Actual Duration
35 | Dial into the meetme lineToll-free: +1-8666923580 Toll: +1-2036070564 Participant Code: 3421269 | DBAR Team | 0 | 2013-07-11 20:00 | 2013-07-11 20:00 | 2013-07-11 20:00 | 2013-07-11 20:00 | 0
36 | Team Dial in To Meeting TECHINAL AND STATUS LINE Toll-free:(866)692-3580; Toll:(203)607-0564 ID# 3421269 | WKAB DBAR TEAM | 0.5 | 2013-07-11 20:00 | 2013-07-11 20:30 | 2013-07-11 20:00 | 2013-07-11 20:30 | 0.5
37 | Break production mirrors | MID STORMAN | 0.5 | 2013-07-11 20:30 | 2013-07-11 21:00 | 2013-07-11 20:30 | 2013-07-11 21:00 | 0.5
38 | Verify that all DB filesystems are mounted in Windsor for both Aetnaprod & Spnode45 | MID STORMAN | 0.5 | 2013-07-11 21:00 | 2013-07-11 21:30 | 2013-07-11 21:00 | 2013-07-11 21:30 | 0.5
39 | WKABPROD checkout of data consistency | Mike Swafford | 0.5 | 2013-07-11 21:30 | 2013-07-11 22:00 | 2013-07-11 21:30 | 2013-07-11 23:00 | 1.5
| DPPRD01 checkout of data consistency | Eugene Berman | 0.5
41 | Rename wkabprod db to WKABDBAR | Mike Swafford | 1 | #REF! | #REF! | 2013-07-12 00:30 | 2013-07-12 00:30 | 0
| Rename DPPRD01 db to DPPDBAR | Eugene Berman | 1
43 | Remove all references to production from WKAB DBAR Server | Mike Swafford | 0.2 | #REF! | #REF! | 2013-07-12 00:30 | 2013-07-12 00:30 | 0
| Remove all references to production from WKAB PeopleSoft Server | Eugene Berman | 0.2
| Validate DPPDBAR Peoplesoft DB is available | Mike Swafford/Eugene Berman | 0.2
46 | Run script to remove all e-mail references | Mike Swafford | 0 | #REF! | #REF! | 2013-07-12 00:30 | 2013-07-12 00:30 | 0
47 | Confirm that SMTP is DISABLED | AIX Eng | 0 | #REF! | #REF! | 2013-07-12 00:30 | 2013-07-12 00:30 | 0
48 | Make sure Workability Production Print servers (MVMPWKPSAP10, MVMPWKPSAP11, MVMPWKPSAP12 & MVMPWKPSAP13) are NOT pointing to the AETHDBAR environment. | Tree | 0.5 | #REF! | #REF! | 2013-07-12 00:30 | 2013-07-12 01:00 | 0.5
49 | Confirm the latest version of WKABdbpsswrd.dll and Web.config are loaded on the Winswkis10 server so that the server can see the AETHDBAR environment. | ADA/Web Eng | 0 | #REF! | #REF! | 2013-07-12 01:00 | 2013-07-12 01:00 | 0
50 | Attach web server to dbar test environment | Web Eng | 0 | #REF! | #REF! | 2013-07-12 01:00 | 2013-07-12 01:00 | 0
51 | TECHNICAL LINE OPEN Team Dial in To Meeting Toll-free:(866)692-3580; Toll:(203)607-0564 ID# 3421269 | WKAB DBAR Team | 0 | #REF! | #REF! | 2013-07-12 01:00 | 2013-07-12 01:00 | 0
52 | Complete Plumbing Check | Shaun Reehl | 0.5 | #REF! | #REF! | 2013-07-12 01:00 | 2013-07-12 01:30 | 0.5
53 | Screen prints from systems check sent to DRPS_C | Shaun Reehl | 0 | #REF! | #REF! | 2013-07-12 01:30 | 2013-07-12 01:30 | 0
54 | Suspend IO Activity through TPCR - Create screen captures of process | Storage Engineer | 0.3 | #REF! | #REF! | 2013-07-12 01:30 | 2013-07-12 01:48 | 0.3
55 | Create screen shots of before disk import and filesystem mounts on DR server | Storage Engineer | 0.3 | #REF! | #REF! | 2013-07-12 01:48 | 2013-07-12 02:06 | 0.3
56 | Import Disk Groups / Mount all Filesystems / Check raw device permissions, owners, and groups if applicable | Storage Engineer | 0.3 | #REF! | #REF! | 2013-07-12 02:06 | 2013-07-12 02:24 | 0.3
57 | Turn over the DBAR Database server to the DBA; Create screen captures of after disk import and filesystem mounts | Storage Engineer | 0.3 | #REF! | #REF! | 2013-07-12 02:24 | 2013-07-12 02:42 | 0.3
58 | Point the DBAR applications to the DBAR database server; create screen captures | Application Engineer |  | #REF! | #REF! | 2013-07-12 02:42 | 2013-07-12 02:42 | 0
59 | Start database(s) - Report any difficulties to Storage Engineer / Server Engineer; create screen captures | DBA |  | #REF! | #REF! | 2013-07-12 02:42 | 2013-07-12 02:42 | 0
60 | Perform the database checkout; create screen captures | DBA |  | #REF! | #REF! | 2013-07-12 02:42 | 2013-07-12 02:42 | 0
61 | DBAR EXERCISE WRAP UP TAKE DOWN and CONCLUSION | Resource | Est. Duration | Est. Start Time | Est. Completion | Actual Start Time | Actual Completion Time | Actual Duration
62 | Shutdown all Databases | DBA | 0.1 | #REF! | #REF! | 2013-07-12 02:42 | 2013-07-12 02:48 | 0.1
63 | Restore all DBAR application configurations to the original settings; create screen shots | Application Engineer | 0.2 | #REF! | #REF! | 2013-07-12 02:48 | 2013-07-12 03:00 | 0.2
64 | Unmount filesystems / deport volume groups | Storage Engineer | 0.2 | #REF! | #REF! | 2013-07-12 02:48 | 2013-07-12 03:00 | 0.2
65 | Unsuspend PPRC mirroring I/O - allow for production to resync all NEW data. *ensure deletion of any unneeded protected data that may have been used for DBAR test disks | Storage Engineer | 0.1 | #REF! | #REF! | 2013-07-12 03:00 | 2013-07-12 03:06 | 0.1
66 | Remove access to DBAR database server; create screen captures | Server Engineer |  | #REF! | #REF! | 2013-07-12 03:00 | 2013-07-12 03:00 | 0
67 | Send all Screen Prints and log files to DRPS | DBAR Team |  | #REF! | #REF! | 2013-07-12 03:06 | 2013-07-12 03:06 | 0
68 | Send out email stating exercise is complete | DRPS |  | #REF! | #REF! | 2013-07-12 03:00 | 2013-07-12 03:00 | 0
69 | Obtain official sign-off from the folks performing the business checkout | Checkout Team |  | #REF! | #REF! | 2013-07-12 03:06 | 2013-07-12 03:06 | 0
70 | Close out Infoplex ticket | DRPS |  | #REF! | #REF! | 2013-07-12 03:00 | 2013-07-12 03:00 | 0
71 | Send out final documentation | DRPS |  | #REF! | #REF! | 2013-07-12 03:06 | 2013-07-12 03:06 | 0
Formulas:
Est. Completion = [Est. Start Time]+[Est. Duration]/24
Est. Start Time = [Est. Completion, row above]